## Estiamtes
Estimation Framework (with sample)
Key | Category | Object Type | Reference-Ratios | Total-Counts | Categorized Counts | Objects/Hr (Can be adjusted) | Hrs/Object (Calculated) | Hours Needed | Notes
1 | Synapse Environment Set up |  |  |  | 1 | 0.2 | 5 | 5 | Create Azure Synapse Resources
2 | SQL Servers Prep & Connectivity (5 Servers) |  |  |  | 5 | 0.25 | 4 | 20 | Prepare SQL Servers (Prod / Test / Dev). Test Migrations in Test Server (s) first before applying to Production Servers
3 | Migration-Tools-Setup with Environments |  |  |  | 1 | 0.2 | 5 | 5 | Set up work station(s) with necessary tools and connectivity to SQL Servers and Azure Synapse.
4 | Code-Migration-DBs-n-Schemas | DBs + Schemas | 100% | 101 | 101 | 5 | 0.2 | 20.2
5 | Code-Migration-Tables-Easy | Tables-Easy | 80% | 6013 | 4810.4 | 200 | 0.005 | 24.052
6 | Code-Migration-Tables-Medium | Tables-Medium | 15% | 6013 | 901.95 | 100 | 0.01 | 9.0195
7 | Code-Migration-Tables-Complex | Tables-Complex | 5% | 6013 | 300.65 | 20 | 0.05 | 15.0325
8 | Code-Migration-Views-Easy | Views-Easy | 70% | 3220 | 2254 | 20 | 0.05 | 112.7
9 | Code-Migration-Views-Medium | Views-Medium | 20% | 3220 | 644 | 5 | 0.2 | 128.8
10 | Code-Migration-Views-Complex | Views-Complex | 10% | 3220 | 322 | 2 | 0.5 | 161
11 | Code-Migration-SPs-Easy | SPs-Easy | 70% | 1911 | 1337.7 | 4 | 0.25 | 334.425
12 | Code-Migration-SPs-Medium | SPs-Medium | 20% | 1911 | 382.2 | 2 | 0.5 | 191.1
13 | Code-Migration-SPs-Complex | SPs-Complex | 10% | 1911 | 191.1 | 0.5 | 2 | 382.2
14 | C0de-Migration - Triggers | Triggers | 100% | 147 | 147 | 2.5 | 0.4 | 58.8
15 | Data-Migration-Tables-Data-Easy | Tables-Easy | 85% | 6013 | 5111.05 | 100 | 0.01 | 51.1105
16 | Data-Migration-Tables-Data-Medium | Tables-Medium | 10% | 6013 | 601.3 | 20 | 0.05 | 30.065
17 | Data-Migration-Tables-Complex | Tables-Complex | 5% | 6013 | 300.65 | 0.5 | 2 | 601.3
2149.8045
Assumptions:
| 1 | Code and Data Migrations Only, including Dev and Unit Test
| 2 | SQL Server to Azure Synapse Migration Tools Will be Utilized (https://github.com/microsoft/AzureSynapseScriptsAndAccelerators/tree/main/Migration/SQLServer)
| 3 | Azure Synapse Pathway Will be Utilized for Code Translations (https://docs.microsoft.com/en-us/sql/tools/synapse-pathway/pathway-release-notes?view=azure-sqldw-latest)
| 4 | Azure Synapse Pathway Translator (or other accelerators) Success Rates are: 90% for Tables, 80% for Views, 60% for Stored Procedures.
|  | Tables | Views | Procs
| Azure Synapse Pathway (ASP) or Other Accelerator Conversion Rate - This %s can be adjusted based on the Code Base | 90% | 80% | 60%
| Easy | Azure Synapse Pathway (ASP) translates without errors. May need to redistribute. | ASP translates without errors. | ASP translates without warnings but easily done with additional manual efforts
| Medium | ASP translates with warnings. Some manual conversions are needed | ASP translates without warnings and errors. Can be corrected with simple changes. | ASP translates without warnings and errors. Can be corrected with simple changes.
| Complex | ASP unable to translate. Considerable Manual efforts needed. | ASP unable to translate. Considerable Manual efforts needed. | ASP unable to translate. Considerable Manual efforts needed.
| Available Tools To use | Purpose | Resource Links
| (1) Assessment (PowerShell) | Get comprehensive inventory of SQL Servers | https://github.com/microsoft/AzureSynapseScriptsAndAccelerators/tree/main/Assessment
| (2) Assessment (SQL Script) | Quick SQL Server Object Counts and Data Sizes | https://github.com/microsoft/AzureSynapseScriptsAndAccelerators/blob/main/Migration/SQLServer/0_Assessment_Dependencies/SQL_Server_DB_ObjCounts_and_Sizes.sql
| (3) Azure Synapse Pathway | Code Translation | Release notes - Azure Synapse Pathway ¦ Microsoft Docs
| (4) Table DDLS Translation (PowerShell) | Translate Table DDLs | https://github.com/microsoft/AzureSynapseScriptsAndAccelerators/tree/main/Migration/SQLServer/1_TranslateTableDDLs
| (5) SQL Server to Synapse Migration Tools | Data Migration | https://github.com/microsoft/AzureSynapseScriptsAndAccelerators/tree/main/Migration/SQLServer
OSE Sample Input
| Requirement ID | Workload Name | Service Type | Activity | # of instances/jobs/Objects | Objects/Hr (Can be adjusted) | Hrs/Object (Calculated) | Total Effort (in hrs) (in hrs) | Assumptions / Comments
1 | REQ-IT-DLP-01 | DW to Synapse - Migration | Environment Set up - Synapse | Synapse Environment Set up | 1 | 0.2 | 5 | 5
2 | REQ-IT-DLP-02 | DW to Synapse - Migration | Environment Set up - SQL Servers | SQL Servers Prep & Connectivity (5 Servers) | 5 | 0.25 | 4 | 20
3 | REQ-IT-DLP-03 | DW to Synapse - Migration | Environment and Tools Set up | Obtain and set up Migration Tools | 1 | 0.2 | 5 | 5
4 | REQ-IT-DLP-04 | DW to Synapse - Migration | Code-Migration-DBs-n-Schemas | Create Databases and Schemas in Synapse | 101 | 5 | 0.2 | 20.2 | Azure Synapse Gen3 Cross DB Query Available Prior to Migration
5 | REQ-IT-DLP-05 | DW to Synapse - Migration | Code-Migration-Tables-Easy | Translate SQL Tables into Azure Synapse Format and Create Tables in Azure Synapse | 12144 | 200 | 0.005 | 60.72 | 80% of Tables are easy
6 | REQ-IT-DLP-06 | DW to Synapse - Migration | Code-Migration-Tables-Medium | Translate SQL Tables into Azure Synapse Format and Create Tables in Azure Synapse | 2277 | 100 | 0.01 | 22.77 | 15% of Tables are medium
7 | REQ-IT-DLP-07 | DW to Synapse - Migration | Code-Migration-Tables-Complex | Translate SQL Tables into Azure Synapse Format and Create Tables in Azure Synapse | 759 | 20 | 0.05 | 37.95 | 5% of Tables are complex
8 | REQ-IT-DLP-08 | DW to Synapse - Migration | Code-Migration-Views-Easy | Translate SQL Views and Create Views in Azure Synapse | 7546 | 20 | 0.05 | 378 | 70% of the Views are easy
9 | REQ-IT-DLP-09 | DW to Synapse - Migration | Code-Migration-Views-Medium | Translate SQL Views and Create Views in Azure Synapse | 2156 | 5 | 0.2 | 431.2 | 20% of the Views are medium
10 | REQ-IT-DLP-10 | DW to Synapse - Migration | Code-Migration-Views-Complex | Translate SQL Views and Create Views in Azure Synapse | 1078 | 2 | 0.5 | 539 | 10% of the Views are complex
11 | REQ-IT-DLP-11 | DW to Synapse - Migration | Code-Migration-SPs-Easy | Translate SQL Stored Procedures and Create Stored Procs in Azure Synapse | 5217.8 | 4 | 0.25 | 1305 | 70% of the Stored Procs are easy
12 | REQ-IT-DLP-12 | DW to Synapse - Migration | Code-Migration-SPs-Medium | Translate SQL Stored Procedures and Create Stored Procs in Azure Synapse | 1490.8 | 2 | 0.5 | 1193 | 20% of the Stored Procs are medium
13 | REQ-IT-DLP-13 | DW to Synapse - Migration | Code-Migration-SPs-Complex | Translate SQL Stored Procedures and Create Stored Procs in Azure Synapse | 745.4 | 0.5 | 2 | 1193 | 10% of the Stored Procs are complex
14 | REQ-IT-DLP-14 | DW to Synapse - Migration | C0de-Migration - Triggers | Migrate SQL Triggers and Implement these Capabilities in Azure Synapse which does not support Triggers | 147 | 2.5 | 0.4 | 368 | Triggers are not supported in Azure Synapse. Need to find alternatives
15 | REQ-IT-DLP-15 | DW to Synapse - Migration | Data-Migration-Tables-Data-Easy | Migrate Tables Data into Azure Synapse and Check Results (Row Counts and Spot Check Data). Trouble shot data issues. | 12903 | 100 | 0.01 | 130 | 85% of Tables are easy
16 | REQ-IT-DLP-16 | DW to Synapse - Migration | Data-Migration-Tables-Data-Medium | Migrate Tables Data into Azure Synapse and Check Results (Row Counts and Spot Check Data). Trouble shot data issues. | 1518 | 20 | 0.05 | 76 | 10% of Tables are medium
17 | REQ-IT-DLP-17 | DW to Synapse - Migration | Data-Migration-Tables-Complex | Migrate Tables Data into Azure Synapse and Check Results (Row Counts and Spot Check Data). Trouble shot data issues. | 759 | 0.5 | 2 | 608 | 5% of Tables are complex
6392.84
0

## SQL_Object_Counts_DB_Sizes
Sample SQL Server(s)
ServerName | NTables | NProcedures | NViews | NTriggers | SizeMB | SizeGB | SizeTB | Notes
Server 1 | 600 | 300 | 500 | 0 | 7814392.89 | 7814.3929 | 7.8144
Server 2 | 1200 | 535 | 643 | 147 | 2596418.16 | 2596.4182 | 2.5964
Server 3 (lift to VM) - Exclude | 613 | 422 | 656 | 0 | 2363126.88 | 2307.74 | 2.48 | Lift and Shift to Azure VM
Server 4 | 3000 | 574 | 821 | 0 | 1563077.63 | 1563.0776 | 1.5631
Server 5 | 600 | 80 | 600 | 0 | 1854099.13 | 1854.0991 | 1.8541
Totals | 6013 | 1911 | 3220 | 147 | 16191114.69 | 16135.7278 | 16.308