## Sheet1
Category | Description | Responsibilities | Reference-Duration | Ref-Customer-Effort-Hrs | Ref-Services-Effort-Hrs
Project Planning | Kick off, Detailed Project Plan, Sprint Tasks, Personnel, First Sprint Details. | Customer-Led-and-Collaborative | 2-3 Weeks | 80 | 80
Tools Setup | Onboarding, Connectivity and Migration Tools Setup | Services | 2-day |  | 16
Infrastructure | Setting up APS, Azure Blob Storage, Polybase, Azure SQLDW, and Azure SQLDW security | Customer-Led-and-Collaborative | 3-5 days | 40 | 16
ETL Jobs & New Data Loading Process | Design and build new data loading process. The process includes job scheduling, existing ETL job changes, and new components that load tables in Azure SQLDW | Customer-Led-and-Collaborative | 4-months | X+ | X
Down Stream Applications/Reports Migration | Down stream applications or reports can stay on-prem, or to be migrated into Azure. This will be decided in architecture design. | Customer-Led-and-Collaborative | 4-months | X+ | X
Code Migration | Convert APS code to run in Azure SQLDW (Tables, Views, and Stored Procedures) | Services | 3-months | X+ | X
Data Migration | Migrate existing APS data to SQLDW | Services | 4-months |  | X+
Deployment | Configure and run prepared meta data and data migration procedures using Migration Tools | Services | 3-months | 40 | 160
Integration and User Acceptance Testing | Integration testing and verification of data. | Customer | 4-months | X+ | X
Project Management and Governance | Customer 75% PM, Services 50% | Customer-Led-and-Collaborative | 4-months | 540 | 360
| Totals |  |  | X | X