## POC-or-MVP-Access
SQL Server DW to Azure Synapse Migration
# | Item | Description | Notes
1 | Portal Access | POC (MVP) team members should all be Contributors or Owners within the Resource Group created for the POC (MVP) | Customer user to set up from Azure portal: portal.azure.com
2 | Azure Synapse Admin | A customer AAD member will need to be the Azure Synapse Admin, the same person can be the Azure Active Directory Admin for Azure Synapse (see item below). | Customer user. Access to the Administrator SQL Login for Azure Synapse
3A | Azure Active Directory (AAD) Admin | A customer AAD member will need to be the Azure Active Directory Admin for Azure Synapse. This user can create AAD users in Azure Synapse (allowing single sign-on using AAD). | Customer user
3B | Azure Active Directory (AAD) User(s) | POC (MVP) Team members should be made Guest users within AAD. If this is not possible then all Portal activities will become the responsibility of the customer POC (MVP) team members. | POC (MVP) team
4A | Azure Synapse Login Access | POC (MVP) team members should each have their own SQL Login or AAD login | POC (MVP) team
4B | Azure Synapse Privileges | POC (MVP) team member should be members of the db_owner database role (i.e. dbo) of the Azure Synapse database. | POC (MVP) team
4C | Azure Synapse Load User(s) | Load User SQL login with resource class as largerc.
4C | Azure Synapse Performance Tester(s) | Load User SQL login with resource class as staticrc50 - staticrc80
5 | Azure Data Lake Store (ADLS) | POC (MVP) team members will need full access to ADLS storage for the POC (MVP) | POC (MVP) team
6 | Azure Data Factory (ADF) | Synapse Load User(s) need full access to ADF | POC (MVP) data loader
7 | Network Connectivity | POC (MVP) Users will need to connect to Azure Synapse database from Azure Data Factory (within Azure), SQL Server Management Studio (from laptop remote) | POC (MVP) team

## POC-or-MVP-Migration-Tasks
SQL Server DW to Azure Synapse Migration
# | Responsible Party | Notes
1 | Customer | Either customer or customer’s chosen Partner (IT provider)
2 | CSA(s) | Microsoft Cloud Solution Architects
3 | POC (MVP) Team | This can be customer led, Microsoft Led, Microsoft Partner Led. In any model customer will always play a key role, as sponsor, SME, and project manager.
Source System Examples: Teradata, Netezza, Exadata, APS/PDW, SQL Server
Source DW to Azure Synapse Migration Task List (Sample)
# | Task(s) | Description | Key Assumptions & Notes | Responsible Parties | Estimated Duration | Duration In Hours | Customer Hours
1 | Project Plan & Onboarding | POC (MVP) Project Plan & Team Onboarding | Customer PM plans and leads the project. Microsoft POC (MVP) team member(s) needs to have a Customer issued Laptop or equivalent access to Customer's environment. | Customer | 0.5 day | 4 | 4
2 | Designate or set up source system for POC (MVP) | Designate or set up non-production Environment as POC (MVP) environment. | Customer is responsible for hardware and licensing fees | Customer | 1-day? | 8 | 8
3 | Set up On-Prem to Azure Connectivity & AzCopy | Configure network connection for AzCopy (or similar) data movement from on-prem to ALDS storage in Azure for POC (MVP) |  | Customer (CSA provides guidance) | 0.5 day | 4 | 4
4A | Prepare Self-Hosted Integration Run Time | Self-Hosted IR On-Prem VM: Recommend Size: 16-32Core, 128GB and have multi-threaded ADF jobs to gain better throughput. | If Azure Data Factory is used for data migration, the local storage requirement can be reduced to 1TB if there are no big tables to move (0.2TB or greater). | Customer (CSA provides guidance) | 1-day? | 8 | 4
4B | Prepare Local Storage | 5-7 times of the Data to be exported from Source System. For example, volume in POC (MVP) Scope (0.7 TB x 7: 4.9TB). | Migration User(s) needs Read and Write Access to the local storage. | Customer (POC (MVP) Team provides guidance) | 1-day? | 8 | 8
5 | Create or designate Migration User(s) in the POC (MVP) Source System | Migration user(s) needs read access and privilege to access schemas, tables, views, functions, and stored procedures. | Customer team members are users of source systems. CSE as back up user | Customer (POC (MVP) Team provides guidance) | 1 hour? | 1 | 1
6 | Create Azure Environment and Access for Migration | Create Azure Subscription, Azure Storage (Azure Data Lake Storage V2), Azure Synapse, and any needed VMs. Azure Data Factory if it is used for data migration. | It is recommended that all required Azure resources to be created in same azure region, under same resource group. One Microsoft POC (MVP) team member needs to be contributor of the Azure Subscription. All POC (MVP) team members need to be contributors to all Azure resources under this Azure Subscription. | Customer (CSA/POC (MVP) Team provides guidance) | 4 hours | 4 | 4
7 | Set up Azure Synapse Environment for Data Migration | Set up technical environments for Data Migration | With Privileges in Azure Environments | Customer & POC (MVP) Team | 4 hours | 4 | 4
8 | Set up On-Prem Work Environment (WorkStation/VM/Laptop) | Set up Windows workstation (laptop) with Current Visual Studio Code (to run PowerShell Scripts), SSMS, and/or Visual Studio. The Workstation user must have administrative privileges to download and setup software/tools. | The Windows workstation must be able to connect Source system, Azure, has Internet Access, has fast access to the on-prem storage set above. | Customer & POC (MVP) Team | 4 hours? | 4 | 4
9 | Set up and test migration tools | Install and set up necessary tools for migration. | Migration team can use customer laptop or Microsoft provided laptop. | POC (MVP) Team | 4 hours | 4 | 4
10 | Script out Source System Tables, Views, and Stored Procedures | Use SSMS | Indexes and statistics will be scripted out into separate T-SQL Scripts. The indexes and statistics will not be migrated. | Customer (POC (MVP) Team provides guidance) | 4 hours | 4 | 4
11 | Translate DDLs and DMLs | Translate Source System Objects (Tables, Views, and Stored Procedures) | Some views and stored procedures may need special handlings performed by Customer team. | POC (MVP) Team & Customer | 2 hours | 2
12 | Execute Translated Synapse T-SQL Scripts | Execute Azure Synapse DDL and DML T-SQL Scripts | This task needs be completed before data migration. | POC (MVP) Team | 2 hours | 2
13 | Create Schemas and Tables (Staging and Target for Reporting) | Create a set of staging tables to store the exported. Create CTAS or Insert Into T-SQL scripts to transfer to Target tables for reporting. | Staging tables are created as Round_Robin Heap Tables for fast data loading. | POC (MVP) Team | 4 hours | 4
14 | Initial Synapse DDL and DML Test | Spot check tables, views, and stored procedures. | Customer test views and stored procedures | POC (MVP) Team | 4 hours | 4
15 | Perform necessary additional Synapse DDL and DML changes | If above test reveals errors in Azure Synapse code, these errors must be specially handled. |  | Customer or POC (MVP) Team | 3-Days | 24
16 | Export Source System data to Azure Storage | Export Source System data and transfer the same into Azure Storage. | We expect up to 20% data rejection. | POC (MVP) Team | 4 hours | 4
17 | Import Data into Synapse Staging Tables | Import data into Azure Synapse from Azure Storage. | Same as above. | POC (MVP) Team | 2-Days | 16
18 | Azure Synapse Performance Optimization | Review and re-design selected Azure Synapse Target tables with different distributions to optimize performance. Microsoft will provide best practices and recommendations at end of POC (MVP). | Optimization is limited to re-distribute small dimension tables and 2 large fact tables. | POC (MVP) Team | 3 days | 24
19 | Develop & Document Best Practices | Derive best practices based on customer workload and Azure Synapse workload optimization features |  | Microsoft | 1 day | 8
20 | Performance Tests (Run T-SQL Scripts) | Performance of several queries will be tested to validate scale. These queries will be run at different DWUs, such as 2000, 3000, 5000, or higher if needed. | Customer will provide T-SQL queries to be run in Azure Synapse. | Customer | 3 days | 24 | 24
[5 empty] | Total Hours | 165 | 73
[5 empty] | Total Days | 20.625
[5 empty] | Before POC (MVP) (Days) | 4
[5 empty] | POC (MVP) Days | 16.625
Add ETL Migration Tasks
# | ETL Job Name | Job Descriptions | Complexity (Simple, Average, Complex) | Hours to Change Code | Estimated Duration | Duration In Hours | Customer Hours
1 |  |  | Simple | 3 | 0.5 day | 4 | 4
2 |  |  | Average | 5 | 1-day? | 8 | 8
3 |  |  | Complex | 10
4
5
6
7
8
Add Downstream Layer Tasks

## Scoping-Exercise
Sample
# | Objectives / Use Cases | Description | Metrics / Success Criteria
1 | Azure Synapse Knowledge Gain | Gain knowledge on setting up Azure Synapse environment, importing data, and scaling, and executing SQL queries. | Customer POC team can operate Azure Synapse (scaling, pause, resume) and execute T-SQL scripts in Azure Synapse
2 | Azure Data Platforms Knowledge Gain | Gain knowledge by establishing end to end architecture with key components such as Azure Data Lake, Azure Data Factory, Azure Synapse, Purview, Power BI, etc.
3 | Prove out the Code and Data Migration Path | POC Architecture, framework, processes, tools, SQL code conversion, and data migration. | All Objects in scope are successfully migrated (tables, views, stored procedures)
4 | Execute Queries in Synapse | Customer team execute T-SQL Scripts (queries) in Azure Synapse via SSMS or Synapse Query Editor (Please identify queries) | Customer POC team members can execute queries in query editor or SSMS
5 | Measure Azure Query Performance | Measure query performance for different levels of DUWs (for example, 2000, 3000, 4000, 5000, 6000) | Purpose is to get the right SLO for production environment
6 | Compare Query Performance | Compare Azure Synapse query performance with performance in source system. Base line numbers: Query 1: x minutes / seconds. Query 2: x minutes / seconds.
7 | Connecting Reporting System to Synapse | Set connectivity from Reporting System (for example PowerBI, Tableau, Cognos, BO
8 | TBD ELT/ETL Related Work or Others
9 | TBD ELT/ETL Related Work or Others
10 | TBD ELT/ETL Related Work or Others
11 | TBD ELT/ETL Related Work or Others
8 | Downstream/report Layer Related Work
9 | Downstream/report Layer Related Work
10 | Downstream/report Layer Related Work
11 | Downstream/report Layer Related Work
# | POC Notes
1 | Migrate DDL and DMLS first from on-prem MPP system to Azure Synapse
2 | Load data into Azure Synapse
3 | Optimize Azure Synapse
4 | Etc.
5 | Etc.
6 | Etc.

## Summary-of-Objects
Use this query to produce a quick summary of your SQL Server Object List.
AzureSynapseScriptsAndAccelerators/SQL_Server_DB_ObjCounts_and_Sizes.sql at main · microsoft/AzureSynapseScriptsAndAccelerators · GitHub
Database / Data Info | Counts / Totals
# Databases | 3
# Schemas (Across databases) | 3
# Tables | 16
# Views | 10
# Stored Procedures | 10
Data Size (TB) | 5.86
Sample Table List
DatabaseName (Source System) | SchemaName (Source System) | TableName (Source System) | Row Count | Table Size (MB) | Table Size (GB) | Table Size (TB)
STG | admin | Table_Name1 | 250 | 2448 | 2.448 | 0.002448
STG | admin | Table_Name2 | 52421507 | 27560 | 27.56 | 0.02756
STG | inventory | Table_Name3 | 2017 | 1584 | 1.584 | 0.001584
STG | sales | Table_Name4 | 3833501 | 567832 | 567.832 | 0.56783
STG | sales | Table_Name5 | 3156667 | 156789 | 156.789 | 0.15679
EDW | admin | Table_Name6 | 340 | 368096 | 368.096 | 0.3681
EDW | admin | Table_Name7 | 73292 | 172336 | 172.336 | 0.17234
EDW | inventory | Table_Name8 | 58785 | 47968 | 47.968 | 0.047968
EDW | sales | Table_Name9 | 23833501 | 2567832 | 2567.832 | 2.5678
EDW | sales | Table_Name10 | 30156667 | 1556789 | 1556.789 | 1.5568
EDW | admin | Table_Name11 | 2117 | 3104 | 3.104 | 0.003104
DataMart | admin | Table_Name12 | 14125 | 4896 | 4.896 | 0.004896
DataMart | admin | Table_Name13 | 2115 | 2592 | 2.592 | 0.002592
DataMart | sales | Table_Name14 | 178958 | 69912 | 69.912 | 0.069912
DataMart | sales | Table_Name15 | 562582 | 308232 | 308.232 | 0.30823
DataMart | inventory | Table_Name16 | 6 | 1512 | 1.512 | 0.001512
Totals |  |  |  | 5859482 | 5859.482 | 5.8595
Sample View List
DatabaseName (Source System) | SchemaName (Source System) | View Name (Source System)
DataMart | inventory | Vw_Name1
DataMart | inventory | Vw_Name2
DataMart | inventory | Vw_Name3
DataMart | inventory | Vw_Name4
DataMart | inventory | Vw_Name5
DataMart | inventory | Vw_Name6
DataMart | inventory | Vw_Name7
DataMart | inventory | Vw_Name8
DataMart | inventory | Vw_Name9
DataMart | inventory | Vw_Name10
Sample Stored Procs List
DatabaseName (Source System) | SchemaName (Source System) | Stored Procedure Name (Source System)
STG | admin | SP_Name1
STG | admin | SP_Name2
STG | inventory | SP_Name3
STG | admin | SP_Name4
STG | inventory | SP_Name5
STG | admin | SP_Name6
STG | inventory | SP_Name7
EDW | admin | SP_Name8
EDW | inventory | SP_Name9
EDW | admin | SP_Name10
Sample Functions List